# Papua New Guinea Country Brief

March 2025

Contents

1	About Pacific Women Lead	3

2	Overview of Pacific Women Lead activities in Papua New Guinea	3

2.1	Pacific Women Lead at SPC	3

2.2	Pacific Women Lead Governance Board	5

2.3	Pacific Women’s Funds	5

2.4	DFAT regional	5

2.5	DFAT bilateral	10

2.6	Pacific Women Lead Enabling Services	16

3	Impact stories and reach data for DFAT bilateral projects	16

3.1	Impact stories	16

3.2	Periodic reach data	16

3.3	Cumulative reach data	16

4	More information and support	17

4.1	Monitoring, evaluation and learning support	17

4.2	Quality Technical Assurance Group (QTAG)	17

4.3	Grant management	17

4.4	Contact and feedback	18

5	Annex 1 Periodic reach data (January – December 2024) for DFAT bilateral projects	19

6	Annex 2 Cumulative reach data (2021 – present) for DFAT bilateral projects	22

# About Pacific Women Lead

Pacific Women Lead (PWL) is a portfolio of regional investments valued at AUD170 million over 5 years (2021 – 2026). PWL aims to advance gender equality and is ambitious in its intent to take a Pacific-led, intersectional and transformative approach to promoting gender equality in the region and bringing new emphasis to strengthening regional action and architecture in support of gender equality.

The goal of PWL is for: Pacific women and girls, in all their diversity, to be safe and equitably share in resources, opportunities and decision-making with men and boys. For more information visit www.pacificwomen.org

# Overview of Pacific Women Lead activities in Papua New Guinea

As at 31 March 2025, 34 Pacific Women Lead projects were being (or had been) implemented in Papua New Guinea, with a total funding of AUD95,659,668.87.

Table 1 shows how each of these projects are linked to the different PWL portfolio components. Through these components, technical support and funding is provided to Pacific women-led civil society organisations, multilateral and regional organisations, government and other stakeholders.

Table 1: Summary of PWL projects in Papua New Guinea as at 31 March 2025

| PWL Components | # of Projects | Ongoing | Completed | Total Funding (AUD) |
| --- | --- | --- | --- | --- |
| PWL at SPC projects | 4 | 4 | - | $1,945,671.57 |
| PWL Governance Board projects | 0 | - | - | - |
| Pacific Women’s Funds projects | 0 | - | - | - |
| DFAT regional and research projects | 10 | 9 | 1 | $42,801,882.75 |
| DFAT bilateral projects | 19 | 10 | 9 | $47,626,422.55 |
| PWLES projects | 1 | - | 1 | $3,285,692 |
| Total | 34 | 23 | 11 | $95,659,668.87 |

## Pacific Women Lead at SPC

The Pacific Community (SPC) is a distinct implementing partner of PWL (known as PWL at SPC) and has a grant agreement with DFAT Canberra, valued at AUD57,600,000. From this total value, SPC provides technical support to Pacific governments, hosts and supports regional convenings and a grants program for its government partners and women’s organisations across the Pacific.

In Papua New Guinea, PWL at SPC funds 4 downstream implementing partners to implement 4 projects.

Table 2: PWL at SPC projects in Papua New Guinea as at 31 March 2025

| No. | Project Name and Partner | Project Description | Value (AUD) / Timeframe | Project Status |
| --- | --- | --- | --- | --- |
| 1 | Barriers to Female Leadership for Staff at Selected Pacific Island Universities, with an emphasis on Science, Technology, Engineering and Mathematics (STEM) (University of South Pacific - USP) | This project aims to establish baselines and catalysing mechanisms to increase the number of women in senior leadership positions in Pacific Island Universities within STEM and beyond. | $415,539.25 2024 - 2025 | Ongoing (new) |
| 2 | Just, Safe, Resilient and Empowered Pacific Communities (Pacific Conference of Churches - PCC) | The Project works to establish a reporting system for member churches to track and report on their gender equality performance, implement a Safe Church policy on zero tolerance of VAWC in church communities and the Code of Conduct and development and roll out of the Pacific regional faith-based EVAWG strategy. The Project also works to increase women’s participation and access in Church leadership and theology, collaboration of women theologians and national, regional Feminist Organisations, development of Church programmes to address masculinity and violence. | $500,000 2024 - 2025 | Ongoing (new) |
| 3 | Sanap Strong, Standing up strong together for a zero-tolerance approach to GBV, Family & Sexual violence, and Child Harm (Kokoda Track Foundation) | Establish an accessible, and essential case management services and counselling support, and medical services, justice processes and repatriation. | $497,899.25 2024-2026 | Ongoing (new) |
| 4 | Shifting the Power Coalition: Pacific Owned, Women-led Early Warning and Resilience (POWER) systems (ActionAid Australia – Nazareth Centre for Rehabilitation and YWCA PNG) | Shifting the Power Coalition (StPC) empowers diverse Pacific women to lead disaster management, humanitarian, and climate action. Through rapid response and core support grants, StPC has enabled women-led networks to drive crisis response, recovery, and advocacy, ensuring inclusive, gender-responsive humanitarian action. | $532,233.07 2022–2025 | Ongoing |

## Pacific Women Lead Governance Board

The PWL Governance Board has 13 members, 12 of whom are from the Pacific region. DFAT’s Assistant Secretary of the Pacific Development Branch is an ex-officio member of the Board.

|  | Tahina Booth is one of the Papua New Guinea representatives on the PWL Governance Board. Ms. Booth is an accomplished tri-international athlete representing Australia in Olympic weightlifting and powerlifting and in the Rugby League for the Papua New Guinea Orchids. Elite sport has instilled in Tahina discipline and leadership, and the many other skills learnt through sport have transferred into Tahina’s professional life. Tahina founded the Grass Skirt Project (GSP), a Papua New Guinea NGO and social enterprise using sport to prevent gender-based violence through collaborative partnerships and innovative health and wellness events for grassroots communities. |
| --- | --- |
|  | Susil Nelson-Kongoi is the second Papua New Guinea representative on the PWL Governance Board. Susil is a senior executive with ExxonMobil PNG with over 15 years’ experience in the development and professional services sector. In addition to her role as ExxonMobil PNG Media and Communications Manager, Ms Nelson-Kongoi is the Chair of Incentive Fund, Vice President (International) of the Business Council of PNG, Chair of the PNG Business Advocacy Network, and Honorary Treasurer on the Board of Coalition for Change. She is actively involved in other non-profit organisations, such as the Business and Professional Women's Association, advocating for the promotion of women’s participation in the economy, respecting women’s rights and ending violence against women and children. Susil has a Bachelor of Commerce from Canterbury University, New Zealand, and also holds a Master of Business Administration from Divine Word University, Papua New Guinea. |

The Board has a $5 million discretionary fund for projects that it can use to add value to and build on existing PWL activities. To date, there have been no projects funded through this component in PNG.

## Pacific Women’s Funds

The Pacific Women’s Funds is made up of 3 feminist organisations: Women’s Fund Fiji, Urgent Action Fund Asia and Pacific and Pacific Feminist Fund.

The Pacific Women Lead Enabling Services (PWLES) is liaising with the Pacific Women’s Fund component and will include projects being funded in PNG under this component in the next update.

## DFAT regional

This section presents information on regional (multi-country) gender activities in Papua New Guinea. These regional gender activities are managed by either DFAT Post in Fiji or DFAT Canberra (Australia).

There are 10 DFAT regional projects implemented by 9 distinct implementing partners in Papua New Guinea. Of these, 9 are ongoing and one has been completed.

Table 3: DFAT regional projects in Papua New Guinea as at 31 March 2025

| No. | Aidworks Number | Project Name and Partner | Project Description | Value (AUD) / Timeframe | Project Status |
| --- | --- | --- | --- | --- | --- |
| 1 | 77821 | Emerging onto the World Stage - Tennis Australia Women and Girls Pacific Extension (Tennis Australia) | This project aims to increase the pipeline of women administrators in tennis across the Pacific. The program, implemented by Tennis Australia in Fiji, PNG, Samoa, Solomon Islands, Tuvalu, and Vanuatu, focuses on professional development and networking opportunities for women in sports leadership. The project seeks to empower women to take on leadership roles, increase opportunities for elite-level competition, and improve governance structures to better support women and girls in tennis across the region. | $1,111,000 2022–2026 | Ongoing |
| 2 | 77520 | Gender responsive Climate Policy and Women’s Climate Leadership in the Pacific (Women’s Environment and Development Organisation) | This project sought to advance Pacific women’s leadership in climate change decision-making through WEDO’s Women Delegates Fund (WDF) program. By providing funding and capacity-building opportunities, the WDF enabled Pacific women to engage meaningfully in global climate discussions, ensuring their perspectives were reflected in critical decision-making processes. The project also aimed to enhance gender-responsive climate policy in the Pacific by strengthening the capacity of National Gender and Climate Change Focal Points through targeted training and resources to support the integration of gender considerations into national climate policies and strategies. | $699,900 2022–2024 | Completed |
| 3 | 74843 | Niu Vaka Pacific Strategy (2018 - 2022) Phase 1 (International Planned Parenthood Federation - IPPF) | The Niu Vaka Pacific Strategy provides a framework and guidance on a life course approach to SRHR in the Pacific. This entails broadening the focus from family planning to services across the life span from pregnancy and prenatal care and pre-menstruation through menopause. It also looks at critical factors for the Pacific including climate change, gender, disability, non-communicable diseases and sexual and gender-based violence. | $500,000 2021 – 2022 | Completed |
|  | 77862 | Core funding to the IPPF Global Strategic Framework (22-26) and Pacific Strategy (22-26) (International Planned Parenthood Federation - IPPF) | IPPF's Pacific Niu Vaka Strategy, Phase II aims to break down barriers and ensure quality sexual and reproductive health and rights (SRHR) are accessible to all in the Pacific. The project focuses on reaching the most marginalised and excluded groups with comprehensive SRHR information and services. It champions the voices of young people and leverages the power of movements and networks to advance SRHR across the region. | $2,000,000 2023–2026 | Ongoing |
| 4 | 74112 | Pacific Partnership to End Violence Against Women and Girls (PPEVAWG) Phase 1 (UN Women) | The Project sought to promote Gender Equality, prevent VAWG, and increase access to quality VAWG response services for survivors. The programme engages with over 100 partners across the region, including national governments, CSOs, EVAWG networks, faith-based groups, and sports associations. | $800,000 2021 – 2023 | Completed |
|  | 77334/8 | Pacific Partnership to End Violence Against Women and Girls Phase 2 (UN Women) | The Pacific Partnership to End Violence Against Women and Girls Phase II aims to promote gender equality, prevent violence, and improve access to services for survivors. The programme supports regional and national leadership to align legislation and policies with international standards, addressing gaps and securing resources for enforcement. It challenges harmful social norms through community engagement and education, with the Social Citizenship Education project working within schools to promote gender equality. The programme strengthens survivor-centred services by enhancing the capacity of health, justice, and social service providers, while empowering women’s rights movements and amplifying the voices of marginalized groups. | $15,934,693.05 2023–2027 | Ongoing |
| 5 | 69294/67 | Pacific Community’s (SPC) Human Rights and Social Development (HRSD) Division Support | This project provides program funding to support the implementation of the SPC HRSD Business Plan 2021-2026. The plan focuses on strengthening inclusive, transparent, and responsive governance and institutions for human rights and social development; promoting gender equality, equity, and social inclusion; preserving and protecting positive cultural expressions; and accelerating impact through knowledge, learning, and innovation. The project aims to achieve a just, equitable, and resilient Pacific Island society by ensuring that state laws, policies, and institutions uphold the rights of all people, providing equitable access to social services and economic opportunities for women, youth, and marginalised groups, promoting non-violence and inclusion in communities, and safeguarding cultural heritage. | $2,700,000 2022–2026 | Ongoing |
| 6 | 76569 | Pilot Pacific Women’s Sports Administration Program (Netball Australia) | This project promotes women's leadership within netball by supporting women in taking on executive, coaching, and decision-making roles. It also aims to increase access to safe and inclusive competition for women and girls across the Pacific, ensuring they can participate in sports free from discrimination or harm. | $1,638,600 2021–2024 | Completed |
|  | TBC | Netball’s Ocean of Power - Strength in Every Wave Phase 2 (Netball Australia) | This project promotes women's leadership within netball by supporting women in taking on executive, coaching, and decision-making roles. It also aims to increase access to safe and inclusive competition for women and girls across the Pacific, ensuring they can participate in sports free from discrimination or harm. | $2,403,991.70 2024 - 2026 | Ongoing |
| 7 | 69294/46 | Progressing Gender Equality in the Pacific (PGEP) (Human Rights and Social Development Division - SPC) | This project focused on strengthening gender mainstreaming by enhancing policy design, implementation, and monitoring to advance gender equality outcomes. It worked to build the capacity of Pacific governments to integrate gender considerations across policies, programs and services. The project also supported improved collection, analysis, and use of gender data and statistics at both country and regional levels. By strengthening data systems, the project aimed to provide evidence that informs policy decisions, tracks progress on gender equality commitments and ensures that the needs and experiences of women and men were accurately represented. | $2,156,401 2021 – 2023 | Ongoing |
| 8 | 78400 | Progressing Pacific Islands Forum (PIF) Gender Equality, Disability and Social Inclusion Priorities (Pacific Island Forum Secretariat) | This project provides funding for the Pacific Islands Forum Women Leaders Meeting (PIFWLM) and supports broader gender equality and disability inclusion efforts by the Secretariat, including the implementation of PIFWLM outcomes and the coordination and monitoring of key regional frameworks such as the revitalised Pacific Leaders Gender Equality Declaration (PLGED), the Pacific Framework on the Rights of Persons with Disabilities (PFRPD), and the Gender Equality and Social Inclusion (GESI) commitments outlined in the 2050 Strategy Implementation Plan. | $3,902,976 2023–2026 | Ongoing |
| 9 | 76453 | RiseUp! Mobilising Young Women's Leadership and Advocacy Phase IV (World YWCA) | Leadership program developed and led by young women for young women, taking into account local contexts and priorities. RiseUp! provides training, networking and peer support to young women between the ages of 18 and 30 years. It supports young women in contexts where their rights and voices are repressed to know and claim those rights within their peer, family and community networks, and to work collectively to mobilise for change. | $6,000,000 2020–2025 | Ongoing |
| 10 | TBC | We Rise Coalition Phase 4 (International Women’s Development Agency - IWDA) | We Rise Coalition Phase 4 is a feminist movement-building project led by six experienced Pacific feminist organizations: femLINKpacific (Fiji), Fiji Women’s Rights Movement (Fiji), Sista (Vanuatu), Voice for Change (PNG), Brown Girl Woke (Samoa), and IWDA (Australia). The Coalition aims to strengthen Pacific feminist organizations and movements by fostering solidarity, empowering new generations of leaders, advocating for gender-transformative policies, and mobilizing resources. | $2,954,321 2024 – 2026 | Ongoing |

## DFAT bilateral

This section provides information on bilateral projects funded and managed by the PNG Women Lead program (PNG Women Lead program is managed by Abt Associates, a managing contractor).

There are 19 projects implemented by14 distinct implementing partners and 6 downstream implementing partners. Of these, 10 are ongoing and 9 have been completed.

Table 4: DFAT bilateral gender projects in Papua New Guinea as at 31 March 2025

| No. | Aidworks number | Project Name and Partner | Project Description | Value (AUD) / Timeframe | Project Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Not provided | Bel Isi PNG (Santos Foundation) | The project aims to galvanize the private sector in partnership with government and civil society to play a transformational leadership role in changing attitudes towards family and sexual violence and improving services for survivors. | $5,009,833.62 2018–2025 | Ongoing |
| 2 | Not provided | Creative Approaches for Impact in International Development (Queensland University of Technology) | Project description not available. | $150,000 2021–2022 | Completed |
| 3 | Not provided | Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 1 (Femili PNG) | Femili PNG established the first case management center in Lae to support survivors to access emergency medical care, access emergency shelter of an adequate duration and standard, provide counselling support and assistance to obtain police, legal and social services if requested. This project is the next phase of support building on, and progress made under the Pacific Women program. | $6,531,621.6 2017 – 2023 | Completed |
|  | 77962 | Funding to Femilli PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 (Femili PNG) | Femili PNG established the first case management center in Lae to support survivors to access emergency medical care, access emergency shelter of an adequate duration and standard, provide counselling support and assistance to obtain police, legal and social services if requested. This project is the next phase of support building on and progress made under the Pacific Women program. | $6,531,621 2023–2027 | Ongoing |
| 4 | 77959 | From Gender Based Violence to Gender Justice and Healing Phase 2 (International Women’s Development Agency) | The project aims to reduce family and sexual violence in Bougainville by addressing the root causes of gender inequality. It does this through supporting Bougainville women’s human rights defenders to lead responses to, and prevention of, family and sexual violence with government and communities; and by enabling men and women to prevent family and sexual violence at community level by promoting shared power and decision making between women and men. | $1,575,755. 2023–2024 | Completed |
|  | Not provided | From Gender-based Violence to Gender Justice and Healing Phase 3 (International Women’s Development Agency) | The project aims to reduce family and sexual violence in Bougainville by addressing the root causes of gender inequality and follows on from the previous Phase II grant agreement and progress. The project strongly aligns with NCfR strategic plan It does this through supporting Bougainville women’s human rights defenders to lead responses to, and prevention of, family and sexual violence with government and communities; and by enabling men and women to prevent family and sexual violence at community level by promoting shared power and decision making between women and men. | $5,428,614.41 2024 - 2027 | Ongoing |
| 5 | Not provided | United for Equality and an End to Gender-based Violence (UN Women) | This project worked with the National Capital District Commission to review the Gender policy and support its implementation. This included the development of tools, supportive workplace approaches with HR, and review of the various community programs including the women's desk at the commission. The United for Equality Summit was a key advocacy and policy dialogue event under the program | $1,000,000 2021–2024 | Completed |
| 6 | Not provided | Responding to Gender Based and Sorcery Related Violence in Highlands of PNG (Oxfam PNG) | This project is preventing violence against women by challenging traditional community attitudes to sorcery, implementing behavioral change activities with communities and conducting research on the effectiveness of repatriation of survivors. | 2021–2022 | Completed |
| 7 | 77960 | Safe Schools Strong Communities Phase 1 (Equal Playing Field) | This project is preventing gender-based violence experienced in schools by building respectful ways of communicating between girls and boys in school, as well as creating an enabling school environment with support and upskilling to teachers. This project is also an interim arrangement to enable EPF to strengthen operationally and the completion of an evaluation to inform future direction. | $690,900 2023–2024 | Completed |
| 8 | Not provided | Safe Communities Project (Equal Playing Field) | This project follows on from the previous Safe Schools, Strong Communities project. The goal of this project is to increase the capacity of communities to prevent and respond to violence against women and children. It also seeks to strengthen EPF organisationally for sustainability. | $2,912,280 2024–2027 | Ongoing |
| 9 | Not provided | Scaling up technical support to Family Support Centers (Family Health International) | Project description not available. | 2021–2022 | Completed |
| 10 | 77830 | Supporting Participatory Democracy in PNG (Australian National University) | Project description not available. | $189,944.88 2022–2023 | Completed |
| 11 | 77842 | Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 (Center for International Private Enterprise) | This project involves two partners, CIPE and the WMRC. The grant aim to establish an entrepreneurial ecosystem for women in PNG to enable women’s economic empowerment. | $3,768,750.04 2021–2024 | Completed |
|  | Not provided | Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 (Center for International Private Enterprise) | This project focuses on the WBRC in NCD by CIPE and follows on from the previous phase of support. The grant aim to establish an entrepreneurial ecosystem for women in PNG to enable women’s economic empowerment. It does so through a focus on women's access to resources through training, skills development and rights awareness and organisational strengthening and sustainability of WBRC. | $376,800 2024 - 2027 | Ongoing |
| 12 | Not provided | Strengthening PNG’s Parliament Project – National Parliament and Bougainville House of Representatives (UNDP) | The Strengthening PNG’s Parliament Project aims to strengthen legislative institutions in PNG by streamlining legislative work, enhancing oversight mechanisms, and fostering openness and public engagement with a particular emphasis on empowering women and facilitating their active participation. This includes the Bougainville House of Representatives and MPs | $500,000 2022–2027 | Ongoing |
| 13 | 77951 | Strengthening the Business Coalition for Women Phase 2 (PNG Business Coalition for Women) | This project supports the Business Coalition for Women to improve the status and safety of women in workplaces. The project is working to empower women economically and improve businesses. This project is the next phase of support building on lessons and progress made under the Pacific Women program. | $ 2,442,300 2023–2027 | Ongoing |
| 14 | Not provided | Partner Development Support Initiative (PNG Women Lead) | This project aims to strengthen organisational capacity of PNGWL partners targeting strategic and technical support for technical gender equality expertise, monitoring and evaluation, communications, and operational strengthening for human resources, planning, finance, risk management, strategic partnerships and business development. | $1,050,000 2024–2027 | Ongoing |
| 15 | Not provided | Protection of Women and Girls during COVID-19 Emergency (UN Women) | The project aims to support safe house services and support prevention activities across target provinces. Its activities evolved over time and included recruitment of the Protection Specialist to oversee the Protection Cluster; development of GBV and Covid risk communications products, and awareness raising. The last extension included supporting safe houses by delivering vouchers/dignity kits for GBV survivors. | $1,000,000 2020–2024 | Completed |
| 16 | Not provided | Woman Leading Change in the Highlands (WLCiH) (IWDA) | The proposal continues the work of IWDA in partnership with VfC under this new project: women leading change in the highlands (WLCiH) 2024-2027 under 4 outcome areas. The WLCiH project builds on the: women’s empowerment and voice for equal rights in PNG project (WEAVERS) 2021-2024 which supported both VfC and Wide Bay Conservation Association (WBCA) in PNG. However, under this new project, IWDA seeks to partner directly with VfC only. The WLCiH project goal, outcomes and activities aim to contribute to VfC strategic plan 2018-2028, including strategic goals 1-4, and the ongoing operation and sustainability of VfC services. The project goal is that women and girls in Jiwaka Province experience increased respect and protection within their communities. | $2,500,000 2024–2027 | Ongoing |
| 17 | NA | Women in Disability Network (WiDN) Support Project (WiDN with PNG Women Lead) | This project aligns with the PNGWL Disability Strategy objective 1 Partnering with OPDs: by providing core and activity funding to support the strengthening of the technical and operational capacity of organisations or networks led by women with disabilities, including their individual leadership capabilities, to advance and advocate for disability reform (including policy) in PNG. | $500,000 2024–2027 | Ongoing |
| 18 | 77830 | Women’s Empowerment and Voice for Equal Rights in Papua New Guinea (IWDA) | This project involves three partners, IWDA, Voice for Change and Wide Bay Conservation. The Project focuses on supporting young women's leadership, supporting access to GBV response services, organisational capacity building of PNG partners, protection of matrilineal land rights of women, women's leadership networks being strengthened. This project also conducts participatory research into the women's rights movement in PNG. | $3,967,853 2021–2024 | Completed |
| 19 |  | Women Make the Change Project: Increased Voice for Women in Political Processes Phase 1 (UN Women) | The project aims to strengthen legal and policy framework that underpins women’s leadership, including promoting temporary special measures for women in politics; including strengthening governance institutions and leaders who are responsible for driving gender equality, women’s empowerment and leadership. The project also works directly with aspiring women leaders and women’s organizations to build their capacities to engage in and influence decision making. | $1,000,000 2021 – 2023 | Completed |
|  | NA | Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 (Un Women) | The project aims to strengthen legal and policy framework that underpins women’s leadership, including promoting temporary special measures for women in politics; including strengthening governance institutions and leaders who are responsible for driving gender equality, women’s empowerment and leadership. The project also works directly with aspiring women leaders and women’s organizations to build their capacities to engage in and influence decision making | $500,149 2024 | Completed |

## Pacific Women Lead Enabling Services

Pacific Women Lead Enabling Services (PWLES) provides whole-of-portfolio monitoring, evaluation and learning oversight, technical advisory support and grant management services. PWLES has an independent Quality and Technical Assurance Group (QTAG) panel of approximately 50 consultants. PWLES is valued at AUD32 million.

PWLES managed one project that was implemented in PNG by one distinct and one downstream implementing partner. We Rise Coalition Phase 3 has completed and is now captured under DFAT regional as We Rise Coalition 4.

Table 5: PWLES projects in Papua New Guinea as at 31 March 2025

| No. | Project Name and Partner | Project Description | Value (AUD) / Timeframe | Project Status |
| --- | --- | --- | --- | --- |
| 1 | We Rise Coalition: Feminist Movement for transformative change Phase 3 (International Women’s Development Agency) | We Rise Coalition Phase 3 focuses on developing, demonstrating, and strengthening feminist coalitions and partnerships to promote inclusive governance, equality, diversity, justice, and women’s human rights. | $3,285,692 2022 – 2024 | Ongoing |

# Impact stories and reach data for DFAT bilateral projects

## Impact stories

Pacific Women Lead Enabling Services (PWLES) engages with the PNG Women Lead program to collect impact stories with bilateral partners in PNG. These stories will be made available online on the PWL website and the link will be included in the next update.

## Periodic reach data

From January to December 2024, 8 projects in PNG provided data against quantitative PWL indicators. See Annex 1 for periodic reach data for DFAT bilateral projects

## Cumulative reach data

Since 2021 to present, 11 projects have provided data against PWL quantitative indicators. See Annex 1 for cumulative reach data for DFAT bilateral projects.

# More information and support

This country brief was prepared by Pacific Women Lead Enabling Services (PWLES). PWLES provides support for DFAT Posts and PWL at SPC in the following ways.

## Monitoring, evaluation and learning support

PWLES manages the PWL portfolio MEL system. The MEL system has two databases:

- A Quantitative database that tracks progress against PWL indicators and can be accessed through a dashboard on the PWL website: Pacific Women Lead - Our Impact. The dashboard is updated six monthly after each reporting cycle.

- A Qualitative database that allows the PWLES MEL team to code partner narrative reports against qualitative change domains.

The MEL system has the capability to organise and provide data, particularly for DFAT’s reporting processes (IMR and Tier 2 reporting), and qualitative evidence or quotes that can be used for briefing documents or speeches.

Collection of qualitative impact stories: PWLES collaborates with partners in each country to collect impact stories twice a year (February and July). These stories are used to inform the PWL MEL system and can be used by the PWL components for public diplomacy. These stories are published on the PWL website: Pacific Women Lead - Stories

Monitoring the rights of people with disabilities Framework: PWLES developed two guidance notes to support partners to enhance data collection and reporting on disability inclusion. The guidance notes can be accessed here: Pacific Women Lead - Resources. PWLES has also facilitated a webinar discussion on these guidance notes which you can watch here: Monitoring the journey towards the realisation of rights for people with disabilities.

Annual Reflection and Analysis Workshop: Each year, PWLES co-convenes an Annual Reflection and Analysis Workshop in September that brings together partners across the PWL portfolio to collaborate and analyse data to understand the program’s progress and make recommendations for the program. A summary of the 2024 Annual Reflection and Analysis Workshop can be watched here: Second Pacific Women Lead Annual Reflection and Analysis Workshop (2024).

Clear Horizon Academy PWL MEL Platform: PWLES has developed 3 training modules with Clear Horizon Academy to support PWL partners:

- Using data for reporting and learning,

- collecting impact stories

- understanding, monitoring and reporting disability inclusion.

These are online and self-paced modules and partners can seek access through the PWLES.

## Quality Technical Assurance Group (QTAG)

Through the QTAG, PWLES provides technical support to smaller DFAT Post in Tuvalu, Kiribati, FSM, Palau, Nauru, Niue, and Republic of Marshall Islands. QTAG currently offers tailored GEDSI support through consultants to smaller DFAT Posts.

## Grant management

PWLES provides program management support to DFAT Posts in smaller countries. Currently, PWLES provides grant management support to:

- Two regional programs: Balance of Power and We Rise Coalition Phase 3,

- Three projects in Tuvalu (funded through the Tuvalu DFAT Post Gender Country Plan), and

- Management of Gender Advisers in Tuvalu (Gender Equality and Social Inclusion Adviser), FSM (Family Protection Adviser) and Palau (Family Protection Act Adviser).

## Contact and feedback

If you have questions or feedback on this country brief, please contact PWLES on info@pwles.org

# Annex 1 Periodic reach data (January – December 2024) for DFAT bilateral projects

| Project title | Indicator | Girls | Girls with disabilities | Women | Women with disabilities | Boys | Boys with disabilities | Men | Men with Disabilities | Not disaggregated | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 22 | 0 | 0 | 0 | 6 | 0 | 0 | 28 |
| Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 5 | 0 | 192 | 0 | 5 | 0 | 45 | 0 | 0 | 247 |
| Bel Isi PNG | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 45 | 0 | 0 | 0 | 36 | 0 | 0 | 81 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 12 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 882 | 23 | 0 | 0 | 8 | 6 | 0 | 919 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 35 | 0 | 0 | 0 | 13 | 0 | 0 | 48 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 |
| Safe Communities Project | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 4 | 0 | 0 | 0 | 10 | 0 | 0 | 14 |
| Bel Isi PNG | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 160 | 0 | 0 | 0 | 77 | 0 | 0 | 237 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of people who participated in sessions on gender issues and women’s equal rights | 109 | 2 | 133 | 16 | 111 | 6 | 134 | 23 | 0 | 534 |
| Safe Communities Project | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 26 | 0 | 0 | 0 | 33 | 0 | 0 | 59 |
| Strengthening the Business Coalition for Women Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 660 | 3 | 0 | 0 | 436 | 0 | 0 | 1099 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 | Number of people who participated in sessions on gender issues and women’s equal rights | 13 | 0 | 647 | 4 | 8 | 0 | 9 | 0 | 0 | 681 |
| Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 52 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of people who participated in sessions on gender issues and women’s equal rights | 876 | 0 | 51 | 0 | 807 | 0 | 42 | 1 | 0 | 1777 |
| Bel Isi PNG | Number of services provided to diverse women and children and other survivors of violence | 45 | 0 | 3164 | 0 | 37 | 0 | 0 | 0 | 0 | 3248 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 818 | 818 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 | 3489 | 0 | 0 | 0 | 0 | 0 | 32 | 3539 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 418 |
| Total |  | 1048 | 2 | 9992 | 47 | 968 | 6 | 873 | 30 | 850 | 13842 |

# Annex 2 Cumulative reach data (2021 – present) for DFAT bilateral projects

Table 7: Cumulative reach data for DFAT bilateral gender projects in Papua New Guinea (2021 to present)

| Project title | Indicator | Girls | Girls with disabilities | Women | Women with disabilities | Boys | Boys with disabilities | Men | Men with disabilities | LGBTQIA+ | Not disaggregated | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthening the Business Coalition for Women Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 1804 | 5 | 0 | 0 | 1152 | 3 | 1 | 773 | 3738 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women and girls participating in civil society and intergovernmental forums | 0 | 0 | 376 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 377 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 205 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 224 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |
| Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 5 | 0 | 192 | 0 | 5 | 0 | 45 | 0 | 0 | 0 | 247 |
| Women Make the Change Project: Increased voices for women in political processes | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 154 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 208 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women and girls supported to assume a leadership role at community, provincial and national | 19 | 0 | 231 | 4 | 0 | 0 | 98 | 0 | 0 | 16 | 368 |
| Bel Isi PNG | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 7 | 0 | 296 | 4 | 8 | 0 | 137 | 3 | 0 | 0 | 455 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 45 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 81 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 16 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 18 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 1734 | 10 | 0 | 0 | 32 | 0 | 0 | 1237 | 3013 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 882 | 23 | 0 | 0 | 8 | 6 | 0 | 0 | 919 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 83 | 1 | 0 | 0 | 29 | 0 | 0 | 0 | 132 |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women who have attained formal qualifications | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 |
| Bel Isi PNG | Number of police, law, and justice officials trained to respond to incidents of EVAWG | 0 | 0 | 22 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 27 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of counsellors graduating from recognized counselling institutions | 0 | 0 | 44 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 88 |
| Bel Isi PNG | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 192 | 0 | 0 | 0 | 56 | 2 | 0 | 0 | 250 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 1 | 0 | 123 | 0 | 13 | 1 | 240 | 1 | 0 | 770 | 1149 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 |
| Safe Communities Project | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 4 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 14 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 |
| Bel Isi PNG | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 160 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 237 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 597 | 3 | 2633 | 5 | 593 | 2 | 677 | 4 | 0 | 379 | 4893 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of people who participated in sessions on gender issues and women’s equal rights | 109 | 2 | 133 | 16 | 111 | 6 | 134 | 23 | 0 | 0 | 534 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 1 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 102 |  | 0 | 0 | 41 | 0 | 0 | 0 | 143 |
| Protection of Women and Girls during COVID 19 Emergency | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 22 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 73 |
| Responding to Gender Based and Sorcery Related Violence in Highlands of PNG | Number of people who participated in sessions on gender issues and women’s equal rights | 41 | 0 | 312 | 0 | 25 | 0 | 213 | 2 | 0 | 0 | 593 |
| Safe Communities Project | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 26 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 59 |
| Safe Schools Strong Communities | Number of people who participated in sessions on gender issues and women’s equal rights | 579 | 1 | 1233 | 0 | 575 | 0 | 1280 | 0 | 0 | 136 | 3804 |
| Scaling up technical support to Family Support Centers | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 118 | 2 | 0 | 0 | 39 | 0 | 0 | 20 | 179 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 | Number of people who participated in sessions on gender issues and women’s equal rights | 13 | 0 | 647 | 4 | 8 | 0 | 9 | 0 | 0 | 0 | 681 |
| Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 52 |  | 0 | 0 | 0 | 0 | 0 | 0 | 52 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of people who participated in sessions on gender issues and women’s equal rights | 878 | 0 | 352 | 1 | 808 | 0 | 308 | 2 | 0 | 135 | 2484 |
| Bel Isi PNG | Number of services provided to diverse women and children and other survivors of violence | 231 | 25 | 4328 | 95 | 156 | 1 | 26 | 5 | 0 | 566 | 5435 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of services provided to diverse women and children and other survivors of violence | 358 | 4 | 1309 | 6 | 202 | 4 | 464 | 2 | 0 | 638 | 2987 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818 | 818 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 1 | Number of services provided to diverse women and children and other survivors of violence | 27 | 1 | 2421 | 0 | 9 | 0 | 270 | 0 | 0 | 989 | 3717 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 | 3489 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 3539 |
| Protection of Women and Girls during COVID 19 Emergency | Number of services provided to diverse women and children and other survivors of violence | 631 | 0 | 1906 | 0 | 352 | 0 | 79 | 5 | 0 | 0 | 2973 |
| Responding to Gender Based and Sorcery Related Violence in Highlands of PNG | Number of services provided to diverse women and children and other survivors of violence | 4 | 0 | 16 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 27 |
| Scaling up technical support to Family Support Centers | Number of services provided to diverse women and children and other survivors of violence | 89 | 0 | 219 | 0 | 9 | 0 | 47 | 0 | 0 | 0 | 364 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of services provided to diverse women and children and other survivors of violence | 14 | 0 | 720 | 7 | 8 | 0 | 90 | 1 | 0 | 151 | 991 |
|  |  | 3603 | 36 | 26719 | 185 | 2882 | 14 | 5867 | 59 | 1 | 6756 | 46167 |
| Strengthening the Business Coalition for Women Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 1804 | 5 | 0 | 0 | 1152 | 3 | 1 | 773 | 3738 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women and girls participating in civil society and intergovernmental forums | 0 | 0 | 376 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 377 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 205 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 224 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 |
| Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 | Diverse women and girls supported to assume a leadership role at community, provincial and national | 5 | 0 | 192 | 0 | 5 | 0 | 45 | 0 | 0 | 0 | 247 |
| Women Make the Change Project: Increased voices for women in political processes | Diverse women and girls supported to assume a leadership role at community, provincial and national | 0 | 0 | 154 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 208 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women and girls supported to assume a leadership role at community, provincial and national | 19 | 0 | 231 | 4 | 0 | 0 | 98 | 0 | 0 | 16 | 368 |
| Bel Isi PNG | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 7 | 0 | 296 | 4 | 8 | 0 | 137 | 3 | 0 | 0 | 455 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 45 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 81 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 16 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 18 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 1734 | 10 | 0 | 0 | 32 | 0 | 0 | 1237 | 3013 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 882 | 23 | 0 | 0 | 8 | 6 | 0 | 0 | 919 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Diverse women entrepreneurs provided with financial and/or business development services | 0 | 0 | 83 | 1 | 0 | 0 | 29 | 0 | 0 | 0 | 132 |
| Strengthening the Business Coalition for Women Phase 2 | Diverse women who have attained formal qualifications | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 |
| Bel Isi PNG | Number of police, law, and justice officials trained to respond to incidents of EVAWG | 0 | 0 | 22 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 27 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of counsellors graduating from recognized counselling institutions | 0 | 0 | 44 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 88 |
| Bel Isi PNG | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 192 | 0 | 0 | 0 | 56 | 2 | 0 | 0 | 250 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 1 | 0 | 123 | 0 | 13 | 1 | 240 | 1 | 0 | 770 | 1149 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 |
| Safe Communities Project | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 4 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 14 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of Men who have undertaken male advocacy training and actively participating to promote GE | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 31 |
| Bel Isi PNG | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 160 | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 237 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 597 | 3 | 2633 | 5 | 593 | 2 | 677 | 4 | 0 | 379 | 4893 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of people who participated in sessions on gender issues and women’s equal rights | 109 | 2 | 133 | 16 | 111 | 6 | 134 | 23 | 0 | 0 | 534 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 1 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 102 |  | 0 | 0 | 41 | 0 | 0 | 0 | 143 |
| Protection of Women and Girls during COVID 19 Emergency | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 22 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 73 |
| Responding to Gender Based and Sorcery Related Violence in Highlands of PNG | Number of people who participated in sessions on gender issues and women’s equal rights | 41 | 0 | 312 | 0 | 25 | 0 | 213 | 2 | 0 | 0 | 593 |
| Safe Communities Project | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 26 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 59 |
| Safe Schools Strong Communities | Number of people who participated in sessions on gender issues and women’s equal rights | 579 | 1 | 1233 | 0 | 575 | 0 | 1280 | 0 | 0 | 136 | 3804 |
| Scaling up technical support to Family Support Centers | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 118 | 2 | 0 | 0 | 39 | 0 | 0 | 20 | 179 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 3 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 |
| Strengthening the Entrepreneurial Ecosystem for Women in PNG Phase 4 | Number of people who participated in sessions on gender issues and women’s equal rights | 13 | 0 | 647 | 4 | 8 | 0 | 9 | 0 |  | 0 | 681 |
| Women Make the Change Project: Increased Voice for Women in Political Processes Phase 2 | Number of people who participated in sessions on gender issues and women’s equal rights | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of people who participated in sessions on gender issues and women’s equal rights | 878 | 0 | 352 | 1 | 808 | 0 | 308 | 2 | 0 | 135 | 2484 |
| Bel Isi PNG | Number of services provided to diverse women and children and other survivors of violence | 231 | 25 | 4328 | 95 | 156 | 1 | 26 | 5 | 0 | 566 | 5435 |
| From Gender Based Violence to Gender Justice and Healing Phase 2 | Number of services provided to diverse women and children and other survivors of violence | 358 | 4 | 1309 | 6 | 202 | 4 | 464 | 2 | 0 | 638 | 2987 |
| From Gender-based Violence to Gender Justice and Healing Phase 3 | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 818 | 818 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 1 | Number of services provided to diverse women and children and other survivors of violence | 27 | 1 | 2421 | 0 | 9 | 0 | 270 | 0 | 0 | 989 | 3717 |
| Funding to Femili PNG to operate the Family and Sexual Violence Case Management Centre Phase 2 | Number of services provided to diverse women and children and other survivors of violence | 0 | 0 | 3489 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 3539 |
| Protection of Women and Girls during COVID 19 Emergency | Number of services provided to diverse women and children and other survivors of violence | 631 | 0 | 1906 | 0 | 352 | 0 | 79 | 5 | 0 | 0 | 2973 |
| Responding to Gender Based and Sorcery Related Violence in Highlands of PNG | Number of services provided to diverse women and children and other survivors of violence | 4 | 0 | 16 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 27 |
| Scaling up technical support to Family Support Centers | Number of services provided to diverse women and children and other survivors of violence | 89 | 0 | 219 | 0 | 9 | 0 | 47 | 0 | 0 | 0 | 364 |
| Women's Empowerment and Voice for Equal Rights in Papua New Guinea (WEAVERs) | Number of services provided to diverse women and children and other survivors of violence | 14 | 0 | 720 | 7 | 8 | 0 | 90 | 1 | 0 | 151 | 991 |
| Total |  | 3603 | 36 | 26719 | 185 | 2882 | 14 | 5867 | 59 | 1 | 6756 | 46167 |

Note that total funding only reflects the grants managed under these components that are being implemented in Papua New Guinea and does not reflect the total value of the components.

Each component is a distinct implementing partner of PWL, which means that organisations have a direct grant agreement with donors or funders.

Budget paid out under Pacific Women Shaping Pacific Development

Budget paid out under Pacific Women Shaping Pacific Development

We Rise Coalition Phase 3 budget comes out of PWLES AUD 32,000,000 budget.